## Overall
| Mar. 5 | Mar. 12 | Mar.19 | Mar. 26 | Apr.2 | Apr. 8 | Apr. 15th | Apr. 23th | Apr. 30th | May 7th | May 14th | May 21st | May 28th | Jun. 4th
Backlog | 59 | 67 | 67 | 70 | 70 | 73 | 66 | 64 | 61 | 56 | 54 | 49 | 55 | 60
In Flow | 17 | 17 | 12 | 20 | 5 | 4 | 3 | 11 | 2 | 10 | 6 | 6 | 10 | 8
Out Flow | 13 | 9 | 12 | 16 | 5 | 1 | 10 | 9 | 5 | 15 | 8 | 11 | 4 | 3
Open | 47
Working | 8
Verify | 4
Returned | 1
| Dec. 11 | Dec.18 | Dec. 25 | Jan. 4 | Jan.8 | Jan.15 | Jan. 22 | Jan.29 | Fe.5 | Feb. 19 | Feb. 26 | Mar. 5 | Mar. 12 | Mar.19 | Mar. 26 | Apr.
Plan | 40 | 35 | 30 | 28 | 27 | 25 | 23 | 20 | 18 | 13 | 10 | 8 | 7 | 5 | 3 | 0

## Progress
| Mar. 5th | Mar. 12 | Mar. 19 | Mar. 26th | Apr. 2nd | Apr. 8th | Apr. 15th | Apr. 23th | Apr. 30th | May. 7th | May.14th | May 21st | May 28th | Jun. 4th
Out | 10 | 6 | 6 | 10 | 4 | 1 | 10 | 11 | 4 | 12 | 5 | 6 | 4 | 3
In | 9 | 14 | 10 | 16 | 5 | 4 | 1 | 6 | 2 | 2 | 5 | 5 | 9 | 3
Backlog | 46 | 54 | 58 | 64 | 65 | 68 | 59 | 54 | 52 | 42 | 42 | 41 | 46 | 46
| Mar. 5th | Mar. 12th | Mar. 19th | Mar. 26th | Apr. 2nd | Apr. 8th | Apr. 15th | Apr. 23th | Apr. 30th | May 7th | May 14th | May 21st | May 28th | Jun. 4th
Out | 3 | 3 | 6 | 7 | 1 | 1 | 0 | 0 | 1 | 3 | 2 | 1 | 0 | 0
In | 8 | 3 | 2 | 4 | 0 | 1 | 2 | 3 | 0 | 2 | 0 | 1 | 1 | 4
Backlog | 13 | 13 | 9 | 6 | 5 | 5 | 7 | 10 | 9 | 8 | 6 | 6 | 7 | 11
| May. 7th | May. 14th | May.21st | May 28th | Jun 4th
Out | 0 | 1 | 4 | 0 | 0
In | 0 | 1 | 0 | 0 | 1
Backlog | 6 | 6 | 2 | 2 | 3
c

## Details-VM
Number | Start Date | End Date | Comments
192969 | 2012-07-17
192992 | 2013-05-21
193648 | 2012-08-31
194161 | 2012-10-09
195291 | 2012-12-17
195386 | 2012-12-26
195415 | 2012-12-26
195518 | 2013-01-08
195975 | 2013-02-05
195983 | 2013-02-05
195990 | 2013-02-05
195992 | 2013-02-05
196216 | 2013-02-19
196305 | 2013-02-26
196328 | 2013-03-19
196343 | 2013-03-05
196518 | 2013-03-11
196521 | 2013-03-11
196561 | 2013-03-11
196585 | 2013-03-11
196593 | 2013-03-11
196602 | 2013-03-11
196657 | 2013-03-19
196659 | 2013-03-12
196816 | 2013-03-25
196841 | 2013-03-25
196872 | 2013-05-14 |  | reassign-back
196954 | 2013-04-02
196965 | 2013-04-02
197246 | 2013-04-23
197678 | 2013-05-07
197880 | 2013-05-14
197927 | 2013-05-14
197958 | 2013-05-28
197975 | 2013-05-21
197997 | 2013-05-21
198116 | 2013-05-28
198117 | 2013-05-28
198130 | 2013-05-28
198150 | 2013-05-28
198151 | 2013-05-28
198160 | 2013-05-28
198179 | 2013-05-28
198196 | 2013-06-04
198237 | 2013-06-04
198251 | 2013-06-04

## Archived-VM
Number | Start Date | End Date
190340 | 2012-04-02 | 2011-05-11
196889 | 2013-03-25 | 2012-04-08
190435 | 2012-04-04 | 2012-05-03
191062 | 2012-04-26 | 2012-05-07
183311 | 2011-07-26 | 2012-05-08
190619 | 2012-04-12 | 2012-05-08 |  | 2012
190620 | 2012-04-12 | 2012-05-08 |  | Mar. 27th | Apr. 3th | Apr. 10th | Apr. 17th | Apr. 24th | May. 1st | May 8th | May 15th | May 22nd | May 29th
191292 | 2012-05-03 | 2012-05-08 |  | 0 | 2 | 0 | 3 | 1 | 0 | 7 | 6 | 2 | 6
191375 | 2012-05-07 | 2012-05-08 |  | 3 | 3 | 8 | 8 | 1 | 4 | 6 | 7 | 8 | 7
191174 | 2012-04-30 | 2012-05-09 |  | 6 | 7 | 15 | 20 | 20 | 24 | 23 | 24 | 30 | 31
191425 | 2012-05-08 | 2012-05-09
178979 | 2011-04-11 | 2012-05-11
189981 | 2012-03-20 | 2012-05-11
190797 | 2012-04-18 | 2012-05-14
190495 | 2012-04-08 | 2012-05-18
191376 | 2012-05-07 | 2012-05-21
189997 | 2012-03-20 | 2012-05-24
190496 | 2012-04-08 | 2012-05-24
191789 | 2012-05-22 | 2012-05-24
190347 | 2012-04-02 | 2012-05-27
191155 | 2012-04-28 | 2012-05-27
191273 | 2012-05-02 | 2012-05-27
191910 | 2012-05-25 | 2012-05-29
192037 | 2012-05-31 | 2012-05-31 | Reassign
191764 | 2012-05-21 | 2012-06-04
191767 | 2012-05-21 | 2012-06-12
191788 | 2012-05-22 | 2012-06-12
192431 | 2012-06-12 | 2012-06-26
192634 | 2012-06-20 | 2012-06-26
192652 | 2012-06-21 | 2012-07-04
190666 | 2012-04-13 | 2012-07-15
192690 | 2012-06-25 | 2012-07-18
192864 | 2012-07-07 | 2012-07-19
193076 | 2012-07-20 | 2012-07-25
193012 | 2012-07-19 | 2012-07-26
193075 | 2012-07-23 | 2012-07-26
192824 | 2012-07-06 | 2012-07-30
192809 | 2012-07-03 | 2012-07-31
193202 | 2012-07-27 | 2012-07-31
193241 | 2012-07-31 | 2012-08-02
193261 | 2012-07-31 | 2012-08-02
190407 | 2012-04-04 | 2012-08-03
192862 | 2012-07-06 | 2012-08-03
192961 | 2012-07-16 | 2012-08-03
193232 | 2012-07-30 | 2012-08-03
192839 | 2012-07-05 | 2012-08-09
193318 | 2012-08-03 | 2012-08-10
193330 | 2012-08-05 | 2012-08-10
193382 | 2012-08-09 | 2012-08-10
193383 | 2012-08-09 | 2012-08-10
193216 | 2012-07-31 | 2012-08-14 | Rejected, new created
193367 | 2012-08-09 | 2012-08-14
190422 | 2012-04-04 | 2012-08-16
193302 | 2012-08-03 | 2012-08-16
193303 | 2012-08-03 | 2012-08-16
193384 | 2012-08-09 | 2012-08-16
193448 | 2012-08-13 | 2012-08-16
190300 | 2012-03-30 | 2012-08-21
193466 | 2012-08-16 | 2012-08-21
191406 | 2012-06-15 | 2012-08-22
192790 | 2012-07-02 | 2012-08-22
192814 | 2012-07-04 | 2012-08-22
192892 | 2012-07-10 | 2012-08-22
193321 | 2012-08-09 | 2012-08-22
193336 | 2012-08-06 | 2012-08-22
193509 | 2012-08-21 | 2012-08-23
193180 | 2012-07-27 | 2012-08-31
193325 | 2012-08-05 | 2012-08-31
193327 | 2012-08-16 | 2012-08-31
193328 | 2012-08-16 | 2012-08-31
193470 | 2012-08-16 | 2012-08-31
193473 | 2012-08-21 | 2012-08-31
190719 | 2012-04-16 | 2012-09-04
193193 | 2012-07-27 | 2012-09-04
193474 | 2012-08-16 | 2012-09-04
193165 | 2012-07-25 | 2012-09-06
193416 | 2012-08-10 | 2012-09-06
193537 | 2012-08-28 | 2012-09-06
190497 | 2012-04-08 | 2012-09-07
191156 | 2012-04-28 | 2012-09-07
192696 | 2012-06-28 | 2012-09-07
193354 | 2012-08-09 | 2012-09-07
193684 | 2012-09-04 | 2012-09-07 | Reasign
193647 | 2012-08-31 | 2012-09-08
192067 | 2012-08-10 | 2012-09-10
193079 | 2012-07-23 | 2012-09-10
193672 | 2012-09-04 | 2012-09-10
193454 | 2012-08-30 | 2012-09-11
193536 | 2012-08-22 | 2012-09-13 | Reasign
193768 | 2012-09-11 | 2012-09-13
193236 | 2012-07-30 | 2012-09-18
193247 | 2012-07-31 | 2012-09-18
193278 | 2012-08-01 | 2012-09-18
193279 | 2012-08-01 | 2012-09-18
193280 | 2012-08-01 | 2012-09-18
193281 | 2012-08-01 | 2012-09-18
193645 | 2012-08-31 | 2012-09-18
191472 | 2012-05-10 | 2012-09-21
194379 | 2012-10-18 | 2012-10-02
193504 | 2012-08-21 | 2012-10-09
193731 | 2012-09-06 | 2012-10-09
193867 | 2012-09-13 | 2012-10-09
193922 | 2012-09-18 | 2012-10-09
193990 | 2012-09-25 | 2012-10-09
193753 | 2012-09-10 | 2012-10-10
193754 | 2012-09-10 | 2012-10-10
189445 | 2012-03-01 | 2012-10-12
191469 | 2012-05-10 | 2012-10-12
191470 | 2012-05-10 | 2012-10-12 | Re-assign
191471 | 2012-05-10 | 2012-10-12
191473 | 2012-05-10 | 2012-10-12
191614 | 2012-05-16 | 2012-10-12 | Reassign back
191766 | 2012-05-21 | 2012-10-12
191960 | 2012-05-28 | 2012-10-12
191961 | 2012-05-28 | 2012-10-12
191962 | 2012-05-28 | 2012-10-12
191993 | 2012-05-30 | 2012-10-12
192066 | 2012-08-10 | 2012-10-12
192286 | 2012-06-07 | 2012-10-12
193237 | 2012-07-30 | 2012-10-12
193305 | 2012-08-08 | 2012-10-12
193353 | 2012-08-09 | 2012-10-12
193697 | 2012-09-04 | 2012-10-12
193756 | 2012-09-10 | 2012-10-12
193984 | 2012-09-25 | 2012-10-12
193989 | 2012-09-25 | 2012-10-12
193994 | 2012-09-25 | 2012-10-12
194207 | 2012-10-09 | 2012-10-12
191958 | 2012-05-28 | 2012-10-15
193677 | 2012-09-04 | 2012-10-15
193884 | 2012-09-18 | 2012-10-15
193959 | 2012-10-09 | 2012-10-15
194108 | 2012-10-09 | 2012-10-15
194144 | 2012-10-09 | 2012-10-15
194145 | 2012-10-09 | 2012-10-15
194178 | 2012-10-09 | 2012-10-15
194284 | 2012-10-12 | 2012-10-15
194289 | 2012-10-12 | 2012-10-15
191378 | 2012-05-07 | 2012-10-16
193885 | 2012-09-18 | 2012-10-16
193940 | 2012-09-19 | 2012-10-16
193374 | 2012-08-09 | 2012-10-18
194102 | 2012-10-09 | 2012-10-18
194323 | 2012-10-15 | 2012-10-18
194386 | 2012-10-18 | 2012-10-22
191996 | 2012-05-29 | 2012-10-23
194068 | 2012-09-25 | 2012-10-23
194333 | 2012-10-15 | 2012-10-30
193882 | 2012-09-18 | 2012-11-02
194336 | 2012-10-15 | 2012-11-02
194408 | 2012-10-22 | 2012-11-02
194468 | 2012-10-30 | 2012-11-02
194146 | 2012-10-09 | 2012-11-06
194272 | 2012-10-12 | 2012-11-06 | Reassign
194480 | 2012-10-30 | 2012-11-06
194492 | 2012-10-30 | 2012-11-06
191626 | 2012-08-10 | 2012-11-12
191826 | 2012-05-24 | 2012-11-12
192434 | 2012-06-12 | 2012-11-12
193288 | 2012-08-06 | 2012-11-12
193570 | 2012-08-28 | 2012-11-12
194083 | 2012-10-09 | 2012-11-12
194332 | 2012-10-30 | 2012-11-12
194387 | 2012-10-18 | 2012-11-12
194471 | 2012-10-30 | 2012-11-12
194481 | 2012-10-30 | 2012-11-12
194554 | 2012-11-06 | 2012-11-12
194555 | 2012-11-06 | 2012-11-12
194625 | 2012-11-12 | 2012-11-20
194388 | 2012-10-18 | 2012-11-27
194453 | 2012-10-23 | 2012-11-27
194513 | 2012-10-30 | 2012-11-27
194762 | 2012-11-20 | 2012-12-04
194776 | 2012-11-20 | 2012-12-04
194777 | 2012-11-20 | 2012-12-04
194214 | 2012-10-09 | 2012-12-11
194774 | 2012-11-20 | 2012-12-11
195059 | 2012-12-04 | 2012-12-11
193621 | 2012-10-12 | 2012-12-17
195135 | 2012-12-11 | 2012-12-17
194099 | 2012-10-09 | 2012-12-18
194563 | 2012-11-06 | 2012-12-18
194741 | 2012-11-20 | 2012-12-18
194778 | 2012-11-20 | 2012-12-18
195252 | 2012-12-11 | 2012-12-18
195248 | 2012-12-11 | 2012-12-26
194114 | 2012-10-09 | 2013-01-04
194297 | 2012-10-12 | 2013-01-08
194298 | 2012-10-12 | 2013-01-08
194538 | 2012-11-02 | 2013-01-08
194773 | 2012-11-20 | 2013-01-08
195344 | 2012-12-17 | 2013-01-08
195407 | 2012-12-26 | 2013-01-08
191535 | 2012-05-12 | 2013-01-15
191785 | 2012-11-06 | 2013-01-15 | Reopen
194758 | 2012-12-17 | 2013-01-15
195487 | 2013-01-04 | 2013-01-15
195366 | 2012-12-18 | 2013-01-22
195377 | 2012-12-26 | 2013-01-22
195390 | 2012-12-26 | 2013-01-22
195549 | 2013-01-08 | 2013-01-22
192172 | 2012-06-28 | 2013-01-29
193437 | 2012-08-13 | 2013-01-29
194084 | 2012-10-09 | 2013-01-29
194391 | 2012-10-18 | 2013-01-29
194612 | 2012-11-12 | 2013-01-29
194751 | 2012-11-20 | 2013-01-29
195058 | 2012-12-04 | 2013-01-29
195230 | 2012-12-11 | 2013-01-29
195264 | 2012-12-17 | 2013-01-29
195271 | 2013-01-15 | 2013-01-29
195471 | 2013-01-04 | 2013-01-29
195474 | 2013-01-04 | 2013-01-29
195493 | 2013-01-04 | 2013-01-29
195705 | 2013-01-23 | 2013-01-29
195711 | 2013-01-23 | 2013-01-29
195768 | 2013-01-23 | 2013-01-29
194686 | 2013-01-15 | 2013-02-05
194831 | 2013-01-04 | 2013-02-05
195269 | 2012-12-17 | 2013-02-05
195298 | 2012-12-17 | 2013-02-05 | reassigned
194703 | 2013-01-15 | 2013-02-19
195519 | 2013-01-29 | 2013-02-19
195724 | 2013-01-23 | 2013-02-19
195755 | 2013-01-23 | 2013-02-19
195786 | 2013-01-29 | 2013-02-19
195883 | 2013-01-29 | 2013-02-19
195885 | 2013-01-29 | 2013-02-19
195926 | 2013-02-05 | 2013-02-19
195952 | 2013-02-05 | 2013-02-19
195985 | 2013-02-05 | 2013-02-19
195986 | 2013-02-05 | 2013-02-19
195987 | 2013-02-05 | 2013-02-19
195988 | 2013-02-05 | 2013-02-19
195989 | 2013-02-05 | 2013-02-19
195998 | 2013-02-05 | 2013-02-19 | Re-assigned
194809 | 2013-01-15 | 2013-02-26
195902 | 2013-02-05 | 2013-02-26
192992 | 2012-07-18 | 2013-03-05 | assign to JCL
193713 | 2012-09-07 | 2013-03-05
194321 | 2012-10-15 | 2013-03-05 | assign to JCL
195454 | 2013-01-04 | 2013-03-05
195709 | 2013-01-23 | 2013-03-05
195799 | 2013-01-29 | 2013-03-05
195919 | 2013-02-05 | 2013-03-05
195935 | 2013-02-05 | 2013-03-05
196084 | 2013-02-19 | 2013-03-05
196201 | 2013-02-19 | 2013-03-05
195788 | 2013-01-29 | 2013-03-11
195903 | 2013-03-05 | 2013-03-11
196329 | 2013-03-05 | 2013-03-11
196379 | 2013-03-05 | 2013-03-12
196514 | 2013-03-11 | 2013-03-12
196601 | 2013-03-11 | 2013-03-12 | reassigned
195370 | 2012-12-18 | 2013-03-19
195444 | 2013-01-04 | 2013-03-19
195844 | 2013-01-29 | 2013-03-19
195951 | 2013-02-05 | 2013-03-19
196031 | 2013-02-26 | 2013-03-19
196336 | 2013-03-05 | 2013-03-19
196117 | 2013-02-26 | 2013-03-26
196540 | 2013-03-11 | 2013-03-26
196653 | 2013-03-12 | 2013-03-26
196655 | 2013-03-19 | 2013-03-26
196683 | 2013-03-19 | 2013-03-26
196687 | 2013-03-19 | 2013-03-26
196771 | 2013-03-19 | 2013-03-26
196774 | 2013-03-19 | 2013-03-26
196797 | 2013-03-25 | 2013-03-26
196890 | 2013-03-25 | 2013-03-26
194321 | 2013-03-05 | 2013-04-02
195389 | 2012-12-26 | 2013-04-02
196560 | 2013-03-11 | 2013-04-02
196741 | 2013-03-25 | 2013-04-02
195994 | 2013-02-05 | 2013-04-15
196341 | 2013-03-05 | 2013-04-15
196528 | 2013-03-11 | 2013-04-15
196744 | 2013-03-19 | 2013-04-15
196875 | 2013-03-26 | 2013-04-15
196916 | 2013-03-26 | 2013-04-15
196933 | 2013-03-26 | 2013-04-15
196937 | 2013-04-02 | 2013-04-15
196977 | 2013-04-02 | 2013-04-15
197074 | 2013-04-08 | 2013-04-15
194721 | 2013-01-15 | 2013-04-23
195934 | 2013-02-05 | 2013-04-23
196235 | 2013-02-19 | 2013-04-23
196408 | 2013-03-05 | 2013-04-23
196709 | 2013-03-26 | 2013-04-23
196737 | 2013-03-19 | 2013-04-23
196769 | 2013-03-26 | 2013-04-23
196908 | 2013-03-26 | 2013-04-23
197059 | 2013-04-08 | 2013-04-23
197065 | 2013-04-08 | 2013-04-23
197077 | 2013-04-15 | 2013-04-23
196768 | 2013-03-26 | 2013-04-30
197239 | 2013-04-23 | 2013-04-30
197256 | 2013-04-23 | 2013-04-30
197295 | 2013-04-23 | 2013-04-30
195292 | 2012-12-17 | 2013-05-07 | re-assign to J9test
195299 | 2012-12-17 | 2013-05-07 | re-assign to J9test
195694 | 2013-01-23 | 2013-05-07 | re-assign to J9test
195706 | 2013-02-19 | 2013-05-07 | re-assign to J9test
196190 | 2013-03-05 | 2013-05-07
196419 | 2013-03-05 | 2013-05-07 | re-assign to J9test
196672 | 2013-03-19 | 2013-05-07
196852 | 2013-03-25 | 2013-05-07
197303 | 2013-04-23 | 2013-05-07 | re-assign to J9test
197601 | 2013-04-30 | 2013-05-07
197628 | 2013-04-30 | 2013-05-07
195541 | 2013-01-08 | 2013-05-14
195589 | 2013-01-15 | 2013-05-14
196376 | 2013-04-02 | 2013-05-14
196824 | 2013-03-25 | 2013-05-14
197558 | 2013-04-23 | 2013-05-14
195265 | 2012-12-17 | 2013-05-21
195266 | 2012-12-17 | 2013-05-21
195360 | 2012-12-17 | 2013-05-21
196287 | 2013-02-26 | 2013-05-21
197721 | 2013-05-14 | 2013-05-21
197888 | 2013-05-14 | 2013-05-21
194317 | 2012-10-12 | 2013-05-28
195864 | 2013-01-29 | 2013-05-28
198004 | 2013-05-21 | 2013-05-28
197707 | 2013-05-07 | 2013-05-28
196650 | 2013-03-11 | 2013-06-04 | Assign to JIT
197985 | 2013-05-21 | 2013-06-04
198148 | 2013-05-28 | 2013-06-04 | Assign to J9test

## Details-JCL
Number | Start Date | End Date | Comments
197066 | 2013-04-08
197132 | 2013-04-15
197157 | 2013-04-15
197297 | 2013-04-23
197683 | 2013-05-07
197837 | 2013-05-21
198058 | 2013-05-28
198223 | 2013-06-04
198224 | 2013-06-04
198254 | 2013-06-04
198259 | 2013-06-04

## Archived-JCL
Number | Start Date | End Date
183311 | 2011-07-26 | 2012-05-08
191292 | 2012-05-03 | 2012-05-08
191375 | 2012-05-07 | 2012-05-08
189981 | 2012-03-20 | 2012-05-11
192739 | 2012-06-27 | 2012-07-26
192789 | 2012-07-02 | 2012-07-26
191407 | 2012-06-14 | 2012-08-03 | Re-assign
193060 | 2012-07-23 | 2012-08-03
192996 | 2012-07-18 | 2012-08-07
193174 | 2012-07-26 | 2012-08-07
191626 | 2012-05-17 | 2012-08-10 | Re-assign
192066 | 2012-05-31 | 2012-08-10 | Re-assign
192067 | 2012-05-31 | 2012-08-10 | Re-assign
193370 | 2012-08-10 | 2012-08-13
193392 | 2012-08-10 | 2012-08-13
193368 | 2012-08-09 | 2012-08-22
193439 | 2012-08-13 | 2012-08-22
193438 | 2012-08-13 | 2012-08-22
193456 | 2012-08-16 | 2012-08-22
193455 | 2012-08-16 | 2012-08-22
193504 | 2012-08-21 | 2012-08-23 | Re-assign
193556 | 2012-08-23 | 2012-08-30
193453 | 2012-08-16 | 2012-08-31
193514 | 2012-08-21 | 2012-08-31
193515 | 2012-08-21 | 2012-08-31
193516 | 2012-08-21 | 2012-08-31
193535 | 2012-08-22 | 2012-09-14
193684 | 2012-09-07 | 2012-09-17
193786 | 2012-09-17 | 2012-10-09
193959 | 2012-09-25 | 2012-10-09 | Reassign
181638 | 2011-06-10 | 2012-10-12
193536 | 2012-09-13 | 2012-10-12 | Reasign
193518 | 2012-08-21 | 2012-10-16
193620 | 2012-08-29 | 2012-10-16
193728 | 2012-09-06 | 2012-10-16
194142 | 2012-10-09 | 2012-10-16
193926 | 2012-09-19 | 2012-10-18
194240 | 2012-10-12 | 2012-10-18
194267 | 2012-10-12 | 2012-10-18
194269 | 2012-10-16 | 2012-10-18
194270 | 2012-10-16 | 2012-10-18
194195 | 2012-10-09 | 2012-10-22
194383 | 2012-10-18 | 2012-10-30
194384 | 2012-10-18 | 2012-11-02
194513 | 2012-10-30 | 2012-11-02 | Move to JVM
194545 | 2012-11-02 | 2012-11-02
194546 | 2012-11-02 | 2012-11-02
194235 | 2012-10-12 | 2012-11-06
194351 | 2012-10-18 | 2012-11-12
194581 | 2012-11-06 | 2012-11-12
193762 | 2012-10-12 | 2012-12-26
191470 | 2012-10-16 | 2012-12-26
194714 | 2012-11-13 | 2012-12-26
194835 | 2012-11-27 | 2012-12-26
194862 | 2012-11-27 | 2012-12-26
194455 | 2012-10-23 | 2012-12-27
194456 | 2012-10-23 | 2012-12-27
194457 | 2012-10-23 | 2012-12-27
194458 | 2012-10-23 | 2012-12-27
194712 | 2012-11-13 | 2013-01-04
194713 | 2012-11-13 | 2013-01-04
194728 | 2012-11-20 | 2013-01-04
195431 | 2013-01-04 | 2013-01-04
194272 | 2012-11-06 | 2013-01-08 | Reassign
194931 | 2012-12-11 | 2013-01-08
194659 | 2012-11-12 | 2013-01-15
195579 | 2013-01-15 | 2013-01-15
195582 | 2013-01-15 | 2013-01-22
193517 | 2012-08-21 | 2013-01-29
195359 | 2012-12-17 | 2013-01-29
195397 | 2012-12-26 | 2013-01-29
195726 | 2013-01-29 | 2013-03-05
195839 | 2013-01-29 | 2013-03-05
196239 | 2013-02-19 | 2013-03-05
194711 | 2012-11-13 | 2013-03-11
196061 | 2013-02-19 | 2013-03-12
196361 | 2013-03-05 | 2013-03-12
196663 | 2013-03-12 | 2013-03-18
195298 | 2013-02-05 | 2013-03-19 | re-assign
195998 | 2013-02-19 | 2013-03-19
196422 | 2013-03-05 | 2013-03-19
196425 | 2013-03-05 | 2013-03-19
196594 | 2013-03-11 | 2013-03-19
195849 | 2013-01-29 | 2013-03-22
196366 | 2013-03-05 | 2013-03-22
196372 | 2013-03-05 | 2013-03-22
196833 | 2013-03-22 | 2013-03-25
196834 | 2013-03-22 | 2013-03-25
196835 | 2013-03-22 | 2013-03-25
196675 | 2013-03-19 | 2013-04-02
196872 | 2013-03-22 | 2013-04-08 | reassign to VM
196424 | 2013-03-05 | 2013-04-30
196719 | 2013-03-19 | 2013-05-07
197199 | 2013-04-23 | 2013-05-07
197313 | 2013-04-23 | 2013-05-07
196429 | 2013-03-11 | 2013-05-14
196872 | 2013-05-07 | 2013-05-14 | reassign
192992 | 2013-03-05 | 2013-05-21 | Reassigned to VM

## Details-JIT
Number | Start Date | End Date | Comments
197745 | 2013-05-07
197757 | 2013-05-07
196650 | 2013-06-04

## Archived-JIT
Number | Start Date | End Date | Comments
197721 | 2013-05-07 | 2013-05-14 | re-assign
197623 | 2013-05-07 | 2013-05-21
197634 | 2013-05-07 | 2013-05-21
197699 | 2013-05-07 | 2013-05-21
197908 | 2013-05-14 | 2013-05-21

## Status
Status | Count | Working Issues
NSIed | 0 | Investigating | 7
Closed&Canceled | 2 | Fixing | 0
Verify | 2 | Fixed | 0
Returned | 6
Working | 7
Open | 37

## Options
COMPONET | STATE | Owner
J9cloud | Open | Ray
classes-cloud | Working | San Hong
J9releng | Return | Gavin
J9vm | Close | Xiang Yu
J9gc | Cancel | Susan
J9fvt | Verify | Xing Liang
| Reassigned | Elijah
Michael
Gavin(J9)
j9backlog
Jason
Mesbah
Graeme
Shi Hui

## Pay_attention
CMVC | Comments

## MF
No. | Owner | Abastract | Status | Comment
194161 | Li San Hong | [MT] Object Leaks Causing Allocation Contexts To Not Be Freed | Open
194321 | Gavin | [MT]java -version crash with -Xrcm:consumer=autoprocess | Open
195265 | Gao Yuan | [MT] jck_runtime_api_nio test failure with 700 mode | Open
195266 | Gao Yuan | [MT] jck_runtime_api_lang test failure with 700 mode | Returned
195298 | Gavin | [MT] jck_runtime_vm_constantpool test failure with 700 mode | Closed | Fixed, waiting for integration
195360 | Li San Hong | [MT] jck_runtime_api_util test failure with 700 mode | Open
195541 | Li San Hong | [MT] intermittent javad test failures | Working
195849 | Gavin | [MT][Perf]Tomcat startup regression running in std mode | Working | Will run the test on 80 build
195998 | Gavin | [MT] Javad failed to start for 2nd user | Closed
196235 | Gao Yuan | [MT]User B can't start javad if user A started before | Working | Patch is in review
196343 | Li San Hong | [MT] Channel has platform specific code without soln for Z | Open
196425 | Gavin | [MT] Only TenantGlobals should be loaded when tenant disabled. | Cancled | Can not reproduce in latest level
196429 | Gavin | [MT] libjlimt27.so can not be resolved from tlda launcher | Open | [MT] libjlimt27.so can not be resolved from tlda launcher
196540 | Li San Hong | [MT] with -Djavad.persistAfterEmptyTime=5 javad keeps exiting | Returned | returned for testing
196687 | Gavin-Ottawa[MT] setting IBM_JAVA_OPTIONS causes javad to exit |  | Open

## Archived Data
2012-VM
Jun. 5th | Jun. 12th | Jun. 19th | June 26th | July 2nd | July 10th | July 17th | July 25th | July 31st | Aug. 7th | Aug. 14th | Aug. 21st | Aug. 28th | Sep. 4th | Sep. 11th | Sep. 18th | Sep. 25th | Oct. 10th | Oct. 16th | Oct. 23rd | Oct. 30th | Nov. 6th | Nov. 13th | Nov. 20th | Nov. 27th | Dec. 4th | Dec. 11th | Dec. 18th | Dec. 26th
3 | 2 | 0 | 2 | 0 | 1 | 1 | 2 | 4 | 7 | 7 | 7 | 8 | 7 | 14 | 9 | 1 | 5 | 36 | 6 | 1 | 8 | 12 | 1 | 3 | 3 | 3 | 7 | 1
4 | 3 | 1 | 3 | 5 | 6 | 2 | 7 | 7 | 12 | 15 | 7 | 3 | 8 | 6 | 5 | 6 | 14 | 9 | 7 | 6 | 5 | 2 | 8 | 0 | 2 | 4 | 13 | 6
32 | 33 | 34 | 35 | 40 | 46 | 47 | 52 | 47 | 54 | 62 | 62 | 57 | 58 | 50 | 46 | 51 | 60 | 33 | 34 | 39 | 36 | 26 | 33 | 30 | 29 | 30 | 36 | 41
2012-JCL
July 31st | Aug. 7th | Aug. 14th | Aug. 21st | Aug. 28th | Sep. 4th | Sep. 11th | Sep. 18th | Sep. 25th | Oct. 10th | Oct. 16th | Oct. 23rd | Oct. 30th | Nov. 6th | Nov. 13th | Nov. 20th | Nov. 27th | Dec. 4th | Dec. 11th | Dec. 18th | Dec. 26th
1 | 4 | 5 | 0 | 6 | 5 | 0 | 2 | 0 | 2 | 6 | 6 | 1 | 5 | 2 | 0 | 4 | 0 | 0 | 0 | 5
1 | 0 | 5 | 9 | 3 | 0 | 2 | 2 | 2 | 2 | 7 | 7 | 1 | 4 | 5 | 1 | 2 | 0 | 1 | 1 | 1
8 | 4 | 4 | 13 | 10 | 5 | 7 | 7 | 9 | 9 | 10 | 11 | 11 | 10 | 13 | 14 | 12 | 12 | 13 | 14 | 10
2013-VM
Jan. 4th | Jan. 8th | Jan. 15th | Jan. 22nd | Jan.29th | Feb. 5th | Feb. 19th | Feb. 26th
1 | 6 | 4 | 4 | 16 | 4 | 15 | 2
7 | 3 | 6 | 8 | 7 | 18 | 5 | 4
47 | 44 | 46 | 50 | 41 | 55 | 45 | 47
2013-JCL
Jan. 4th | Jan. 8th | Jan. 15th | Jan. 22nd | Jan. 29th | Feb. 5th | Feb. 19th | Feb. 26th | Mar. 5th | Mar. 12th | Mar. 19th | Mar. 26th | Apr. 2nd | Apr. 8th | Apr. 15th | Apr. 23th | Apr. 30th | May 7th
4 | 2 | 2 | 1 | 4 | 0 | 0 | 0 | 3 | 3 | 6 | 7 | 1 | 1 | 0 | 0 | 1 | 3
1 | 1 | 2 | 0 | 3 | 1 | 3 | 0 | 8 | 3 | 2 | 4 | 0 | 1 | 2 | 3 | 0 | 2 | 2
7 | 6 | 6 | 5 | 4 | 5 | 8 | 8 | 13 | 13 | 9 | 6 | 5 | 5 | 7 | 10 | 9 | 8
All
Dec. 11 | Dec.18 | Dec. 25 | Jan. 4 | Jan.8 | Jan.15 | Jan. 22 | Jan.29 | Fe.5 | Feb. 19 | Feb. 26
43 | 50 | 51 | 54 | 50 | 52 | 55 | 45 | 60 | 52 | 55
0 | 14 | 7 | 8 | 4 | 8 | 8 | 10 | 19 | 8 | 4
0 | 7 | 6 | 5 | 8 | 6 | 5 | 20 | 4 | 15 | 2